## Time
Task | Total Days | Dev Days | Test Days | Status
1. Creating the SDL/Open GL Basic engine | 13 | 9.5 | 3.5
1.1 Create a basic project linking SDL and Open GL together | 2 | 1.5 | 0.5
1.2 Create 2d camera | 2 | 1.5 | 0.5
1.3 Render a sprite to the screen | 1 | 0.5 | 0.5
1.4 Render a plane of sprites with custom width | 2 | 1.5 | 0.5
1.5 Add camera up down left right movement | 1 | 0.5 | 0.5
1.6 Add camera zoom | 2 | 1.5 | 0.5
1.7 Create simple text renderer to display GUI/debug information | 3 | 2.5 | 0.5
2. Create the Nerual Nets Basics | 17 | 11.5 | 5.5
2.1 Create layer types for the nerual net(as matrixes) | 4 | 3 | 1
2.2 Create weight connection for layers (as matrices) | 3 | 2 | 1
2.3 Create forward pass of the nerual net | 3 | 2 | 1
2.4 Compute the matrix calculations on the GPU with shaders | 5 | 4 | 1
2.5 Test which solution is faster(CPU or GPU) | 2 | 0.5 | 1.5
3. Create a basic world generation | 10 | 8 | 2
3.1 Allow the renderer to render a world from a file or tilemap | 5 | 4 | 1
3.2 Create a basic randomiser to create a world with a random set of items in random locations(trees, grass, bushes, rocks) | 5 | 4 | 1
4. First basic species | 47 | 34 | 13
4.1 Create the Species class that holds the generic meta data for a species | 2 | 1 | 1
4.2 Create a Member class that contains the data and state for a memebr of the species | 5 | 4 | 1
4.3 Render the member to the screen via the member class | 1 | 0.5 | 0.5
4.4 Create the eye sight sensor for the members | 7 | 5 | 2
4.5 Create the phsyical needs for the members | 7 | 5 | 2
4.6 Create the emotions for the members that get update depending on physical need | 7 | 5 | 2
4.7 Hook in the nerual net with inputs being the sensors and the emotions | 12 | 9 | 3
4.8 Create a function so that members can MoveTo a tile | 2 | 1.5 | 0.5
4.9 Create a eat function | 4 | 3 | 1
5. Create the game loop and simulation | 5 | 2.5 | 2.5
5.1 Create a loop the incremenets a simulation step | 2 | 1 | 1
5.2 Have each member perform one action per simulation step and then update their state | 3 | 1.5 | 1.5
6. Evolution Algorithm | 53 | 40.5 | 12.5
6.1 Create a merge function for two nerual nets that allows for mutation | 10 | 7 | 3
6.2 Create a function for the Members that allows them to mate | 13 | 10 | 3
6.3 Create a nerual net end point so the members can decide to mate | 5 | 3.5 | 1.5
6.4 Design/Create some sort of attracitvness function that defines who the members mate with. | 25 | 20 | 5
7. Extra Goals | 0 | 0 | 0
7.1 Create more decisions that the Members can do (Build, Mine, Chop Tree…) | 0 | 0 | 0
7.2 Create a species creation screen that allows the player to create different starting species | 0 | 0 | 0
7.3 Create levels the player has to complete | 0 | 0 | 0
7.4 Add sounds | 0 | 0 | 0
7.5 Increase game feel | 0 | 0 | 0
Total Days Assigned: | 145
Total Dev Days Assigned: | 106
Total Test Days Assigned | 39
Total Days Left: | 33

## Risks
Task | Likelihood | Severity | Score | Risk | How can I prevent | How can I mitigate
1.1 Create a basic project linking SDL and Open GL together | 1 | 3.5 | 3.5 | May take longer than planned to understand how to work with the two technologies | Create a practise project to learn the basics | Use the C++ game engine supplied for the ADV Games Tech coursework
1.2 Create 2d camera | 1 | 3.5 | 3.5 | This may not be as simple as I have planned it to be and so take a longer time to complete | Follow a online tutorial to setup the camera and research a the correct camera I need. | Look at how the camera is setup in the ADV Games Techo coursework for the UI elements.
1.3 Render a sprite to the screen | 1 | 4 | 4 | Same as above | - | -
1.4 Render a plane of sprites with custom width | 2 | 1 | 2 | Developing the algorithm to render the sprites to a plane may be more complex then planned for | Chances are low but I will follow an online tutorial. | Ignore this task as we do further work on loading a tilemap later on.
1.5 Add camera up down left right movement | 2.5 | 1.5 | 3.75 | I can't implement this as quickly as planned. | I can take away from test days for this task as it will be tested during play of the game for other elements. | Do not setup the camera right away and move onto other tasks.
1.6 Add camera zoom | 2.5 | 1.5 | 3.75 | Same as above | - | -
1.7 Create simple text renderer to display GUI/debug information | 3 | 1.5 | 4.5 | Text interfers with rendered sprites due to having only one camera. | I'm not sure if this is valid, but in the case it is I will simply create a second camera to render the UI elements | Look at how the camera is setup in the ADV Games Techo coursework for the UI elements.
2.1 Create layer types for the nerual net(as matrixes) | 3 | 5 | 15 | It is more difficult than I imagined to create non-dense layers | Look into other solutions online of people who have implemented nerual nets using C++ | Only work with dense nets to begin with as I know I can create them
2.2 Create weight connection for layers (as matrices) | 4 | 5 | 20 | Similar to above that I may find it difficult to create non dense networks | Same as above | Only work with dense nets to begin with as I know I can create them
2.3 Create forward pass of the nerual net | 2 | 5 | 10 | Figuring out the matrix calculations takes longer then expected | Look online to how to solve | Subtract time from step 2.5 to complete this task.
2.4 Compute the matrix calculations on the GPU with shaders | 4 | 2 | 8 | This is an experiment for me, and so it may go wrong and I may not have allocated enough time. | Research into GLSL before starting development on step. | We skip this and do the foreward pass on the CPU
2.5 Test which solution is faster(CPU or GPU) | 4 | 2 | 8 | The above step isn’t completed | Same as above | Same as above
3.1 Allow the renderer to render a world from a file or tilemap | 3.5 | 3.5 | 12.25 | As I need to develop the algorithm for this and develop it, I may not have enough time to create a serialisable world. | Start with the simiplies solution first, which may be parsing a text file and then loading the correct tile depending on that. Seems I could parse a text file into a 2D array very easily. | Create a static world that doesn't change, this way I won't need this step.
3.2 Create a basic randomiser to create a world with a random set of items in random locations(trees, grass, bushes, rocks) | 3 | 2 | 6 | If the above step doesn't happen, this becomes void. | Same as above | Same as above
4.1 Create the Species class that holds the generic meta data for a species | 2.5 | 5 | 12.5 | I havn't allocated enough time to design the class properly. | Try and design the class as I go whilst working on other areas. | Take time away from task 6.2
4.2 Create a Member class that contains the data and state for a memebr of the species | 3.5 | 5 | 17.5 | Same as above | Create a UML diagram before development work so I don't get lost in the C++ code when developing. | Take time away from task 6.2
4.3 Render the member to the screen via the member class | 1 | 4 | 4 | The member sprite doesn't render correctly above the tilemap | Getting the render order correct | This is a simple risk and so no mitagation is required
4.4 Create the eye sight sensor for the members | 4 | 3.5 | 14 | As I have to design and develop this, it may be too complex to do in the time. | Create UML diagram before development, outline the specifications of what this sensor will do before development. | Simplfy the sensor such that it only proviedes the location of items X distance away from the memebr
4.5 Create the phsyical needs for the members | 3 | 3 | 9 | I overcomplicate this and try to create too much. | Set a small amout of phsyical needs. | Look at other games and what they have used, such as Sims.
4.6 Create the emotions for the members that get update depending on physical need | 5 | 3.5 | 17.5 | Balancing the emotions with the level of the phsyical need is too complicated an equation | Designing the equation before beginning development. | Either have emotions change by a set amount per step, or scrap this idea.
4.7 Hook in the nerual net with inputs being the sensors and the emotions | 4 | 3.5 | 14 | Too much input information for the net to produce any worthwhile results without a lot of training | Test if this is a problem, and if it is take the time to train an initial network that I will use as a starting point going forward. Skipping the initial training phase for the player | Simplfy the inputs to just the emotions and use the sensors just for completing actions.
4.8 Create a function so that members can MoveTo a tile | 2.5 | 1 | 2.5 | Implementing A* takes longer the predicted | Follow an online tutorial | Can skip this step and have members teleport to the place they want to be, walking isn't a key part of the simulation.
4.9 Create a eat function | 1 | 1 | 1 | Over estimated the complexity of this task which may lead to other tasks below having less planned time | I feel at the moment it is correct, but I will aim to achieve this as fast as possible | Any extra time can be alloted where needed
5.1 Create a loop the incremenets a simulation step | 1.5 | 2.5 | 3.75 | Timing the loop so that one step happens in a human watchable amount of time isn't something I have a solution for | Looking at fixed upated time loops, maybe there is a solution there | Hack in something to force a step to only update once a second. This may then need to fire update triggers to all the members
5.2 Have each member perform one action per simulation step and then update their state | 1.5 | 3 | 4.5 | State update is more complicated than I've imagined. | Design the state update before development starts | Take time away from task 6.2
6.1 Create a merge function for two nerual nets that allows for mutation | 3 | 5 | 15 | The merge algorithm doesn't produce similar networks | It's a well documented algorithm and so I will be able to find something online to help | Choose a random selection of nodes to take from each parent and keep the structure the same as one of the parents.
6.2 Create a function for the Members that allows them to mate | 3 | 5 | 15 | This function depends on a attricvness score which is calcualted differently for every member. This could either be too expesnive, or not work as expected. | Design the function before development, and use the testing time properly to check the performance impact. | Remove the attricvness idea and just have them mate with closest other member that wants to mate.
6.3 Create a nerual net end point so the members can decide to mate | 2 | 4 | 8 | In my mind this is very simple, but it may not turn out to be. | Start work on this on time. | Use some of the remaining free days of which there about 30.
6.4 Design/Create some sort of attracitvness function that defines who the members mate with. | 4 | 5 | 20 | Same as 6.2 | Same as 6.2 | Same as 6.2
7.1 Create more decisions that the Members can do (Build, Mine, Chop Tree…) |  |  |  | Wont include risks as this are extra goals | - | -
7.2 Create a species creation screen that allows the player to create different starting species |  |  |  | Wont include risks as this are extra goals | - | -
7.3 Create levels the player has to complete |  |  |  | Wont include risks as this are extra goals | - | -
7.4 Add sounds |  |  |  | Wont include risks as this are extra goals | - | -
7.5 Increase game feel |  |  |  | Wont include risks as this are extra goals | - | -